## Sheet1
Tasks | Expected Date | Actual Date
Design and implement document parsing and preprocessing | June 14, 2023
Doing Prompt engineering for GPT-3.5-turbo | June 16, 2023
Implement GPT-3.5-turbo API calls and response handling | June 19, 2023
Extract and process compliance-related data from GPT-3.5-turbo responses | June 21, 2023
Implement data validation and error handling | June 23, 2023
Design and develop API for UI to use | June 26, 2023
Test the API with various document types and compliance scenarios | June 29, 2023
Optimize the API based on testing feedback and performance metrics | July 3, 2023
Develop documentation and user guides | July 5, 2023