## Sheet1
Tasks | Expected Date | Actual Date
Define project scope and requirements | June 13, 2023
Collect and preprocess historical error pattern data | June 16, 2023
Analyze error patterns and identify solution strategies | June 20, 2023
Set up GPT-Davinci model fine-tuning environment | June 22, 2023
Prepare training data for fine-tuning the GPT-Davinci model | June 26, 2023
Fine-tune the GPT-Davinci model on the prepared training data | June 30, 2023
Evaluate the fine-tuned model's performance on a validation dataset | July 4, 2023
Implement error submission and preprocessing for user input | July 6, 2023
Develop a query generation strategy for the fine-tuned GPT-Davinci model | July 10, 2023
Implement API calls and response handling for the fine-tuned model | July 12, 2023
Extract and process error solutions and recommendations from model responses | July 14, 2023
Implement data validation and error handling | July 17, 2023
Design and develop API for UI to use | July 19, 2023
Test the API with various error types and scenarios | July 21, 2023
Optimize the API based on testing feedback and performance metrics | July 25, 2023
Develop documentation and user guides | July 27, 2023